## Sheet1
Project Name: Procurement Management System
Developed by: Ashiqur Rahman Sami
Supervised by: Shamim Hossain Razu
Sponsored by: BJIT Academy
# | Task Module | Features To be implemented | Activities to be done | Estimated Hours | Start Date | End Date | Module Total (man-month)
Week 1
1 | Project Initiation | 1.1 Project Definition | 1.1.1 Purpose and goals of the project | 1 | 03.02.25 | 03.02.25
|  |  | 1.1.2 Project scope and constraints | 1 | 03.02.25 | 03.02.25
|  | 1.2 Project Charter | 1.2.1 Project timeline | 1 | 03.02.25 | 03.02.25
|  |  | 1.2.2 Project resources | 1 | 03.02.25 | 03.02.25
|  |  | 1.2.3 Project risks and assumptions | 4 | 03.02.25 | 03.02.25
2+A15:E27 | Requirements Analysis | 2.1 Documenting Requirements | 2.1.1 Get requirements from trainers | 2 | 04.02.25 | 04.02.25
|  |  | 2.1.2 Validating Requirements | 1 | 04.02.25 | 04.02.25
|  |  | 2.1.3 Analyzing Requirements | 2 | 04.02.25 | 04.02.25
|  | 2.3 Prepare SRS | 2.3.1 Functional Requirements | 1 | 04.02.25 | 04.02.25
|  |  | 2.3.2 Non-Functional Requirements | 1 | 04.02.25 | 04.02.25
|  |  | 2.3.3 Project Scopes | 1 | 04.02.25 | 04.02.25
3 | Development | 3.1 Backend Development | 3.1.1 Odoo Module Development | 2 | 05.02.25 | 05.02.25
|  |  | 3.1.2 API Development for portal | 16 | 06.02.25 | 07.02.25
Week 2
|  | 3.2 Database Design | 3.2.1 Design of database tables and relationships | 4 | 05.02.25 | 05.02.25
|  |  | 3.2.2 Database Implementation | 2 | 05.02.25 | 05.02.25
|  | 3.3 Front End Development | 3.3.1 Develop Supplier Portal UI | 16 | 10.02.25 | 11.02.25
|  |  | 3.3.2 Develop Approver UI | 4 | 12.02.25 | 12.02.25
|  |  | 3.3.3 Develop Reviewer UI | 4 | 12.02.25 | 12.02.25
|  | 3.4 Feature Development | 3.4.1 Email Verification with OTP | 8 | 13.02.25 | 13.02.25
|  |  | 3.4.2 Supplier Registration Form | 8 | 14.02.25 | 14.02.25
Week 3
|  |  | 3.4.3 Two-Step Verification Process | 8 | 17.02.25 | 17.02.25
|  |  | 3.4.4 RFP Creation and Quotation Submission | 16 | 18.02.25 | 19.02.25
|  |  | 3.4.5 Report Preparation | 8 | 20.02.25 | 20.02.25
|  |  | 3.4.6 Dashboard Preparation | 6 | 21.02.25 | 21.02.25
|  |  | 3.4.7 Deliverables Preparation | 2 | 21.02.05 | 21.02.25
Week 4
4 | Deployment | 4.1 Environment Setup | 4.1.1 Docker Container Setup | 4 | 24.02.05 | 24.02.05
|  |  | 4.1.2 Nginx Configuration | 4 | 24.02.25 | 24.02.25
|  | 4.2 System Deployment | 4.2.1 Odoo Deployment | 2 | 25.02.25 | 25.02.25
|  |  | 4.2.2 Database Deployment | 2 | 25.02.25 | 25.02.25
5 | Project Closure | 5.1 Final Review | 5.1.1 Requirement Validation | 2 | 26.02.25 | 26.02.25
|  |  | 5.1.2 Stakeholder Sign-off | 1 | 26.02.25 | 26.02.25